## Sheet1
| Item or Sequence | Code | Description | Folder | Area | Category | Subcategory | Revision | Expected First Issue Date | Replanned First Issue Date | Fisrt Issue Date | Last Issue Date | Expected Approval Date | Replanned Expected Approval | Approval Date | Contractor / Supplier | MDL Revision | Status | Unnamed: 18 | Expected First Issue Date_parsed | Replanned First Issue Date_parsed | Fisrt Issue Date_parsed | Last Issue Date_parsed | Expected Approval Date_parsed | Replanned Expected Approval_parsed | DaysNoAnswer
2 | 3 | ATL-BDD-23134-PLA-PG-03 | Project Planning - Carta Gantt | EQUIPMENT | BESS | EQUIPMENT | General |  | 29/03/2024 |  |  |  | 26/04/2024 |  |  | SUNGROW | 0 |  |  | 2024-03-29 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-04-26 | 2050-01-01 | -9213
117 | 118 | ATL-BDD-ELE-ET-1431 | ESPECIFICACIÓN SCADA | EQUIPMENT | BESS | EQUIPMENT | SCADA and PPC |  | 01/07/2024 |  | 10/07/2024 |  | 29/07/2024 |  |  | CJR | 1 |  |  | 2024-07-01 | 2050-01-01 | 2024-07-10 | 2050-01-01 | 2024-07-29 | 2050-01-01 | -9213
367 | 368 | ATL-BDD-ELE-ES-1530 | NCS ESTUDIO DE AJSUSTE DE PROTECCIONES CELDAS MT | EQUIPMENT | BESS | EQUIPMENT | Studies |  | 08/11/2024 |  |  |  | 29/11/2024 |  |  | CJR | 20 |  |  | 2024-11-08 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-11-29 | 2050-01-01 | -9213
125 | 126 | ATL-BDD-ELE-LS-1423 | LISTADO DE MATERIALES ELECTRICOS | ELECTRICAL | BESS | ELECTRICAL | General |  | 15/08/2024 |  |  |  | 13/09/2024 |  |  | CJR | 18 |  |  | 2024-08-15 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-09-13 | 2050-01-01 | -9213
126 | 127 | ATL-BDD-ELE-LS-1425 | LISTA DE SEÑALES A SCADA REMOTO ATLAS (N3) | EQUIPMENT | BESS | EQUIPMENT | SCADA and PPC |  | 01/07/2024 |  |  |  | 29/07/2024 |  |  | CJR | 1 |  |  | 2024-07-01 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-07-29 | 2050-01-01 | -9213
365 | 366 | ATL-BDD-ELE-ET-1528 | NCS HOJA DE DATOS CELDAS MT HDTG | EQUIPMENT | BESS | EQUIPMENT | MV Equipment |  | 16/08/2024 |  |  |  | 13/09/2024 |  |  | CJR | 20 |  |  | 2024-08-16 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-09-13 | 2050-01-01 | -9213
364 | 365 | ATL-BDD-ELE-ET-1527 | NCS HOJA DE DATOS DE PROTECCION | ELECTRICAL | BESS | ELECTRICAL | General |  | 16/08/2024 |  |  |  | 13/09/2024 |  |  | CJR | 20 |  |  | 2024-08-16 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-09-13 | 2050-01-01 | -9213
358 | 359 | ATL-BDD-ELE-ET-1521 | NCS HOJAS DE DATOS TECNICOS GARANTIZADOS HDTG | ELECTRICAL | BESS | ELECTRICAL | Auxiliary System |  | 16/08/2024 |  |  |  | 13/09/2024 |  |  | CJR | 20 |  |  | 2024-08-16 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-09-13 | 2050-01-01 | -9213
355 | 356 | ATL-BDD-CC-DW-1912 | DIAGRAMAS DE RED (SUBREDES Y VPN) | EQUIPMENT | BESS | EQUIPMENT | SCADA and PPC |  | 19/07/2024 |  |  |  | 16/08/2024 |  |  | CJR | 16 |  |  | 2024-07-19 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-08-16 | 2050-01-01 | -9213
354 | 355 | ATL-BDD-CC-DW-1911 | MODELADO DE PLANTA | EQUIPMENT | BESS | EQUIPMENT | SCADA and PPC |  | 30/07/2024 |  |  |  | 30/08/2024 |  |  | CJR | 16 |  |  | 2024-07-30 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-08-30 | 2050-01-01 | -9213
165 | 166 | ATL-BDD-ELE-MC-1622 | CS-MEMORIIA TRAFO SSAA | ELECTRICAL | BESS | ELECTRICAL | Switching Building |  | 30/06/2024 |  |  |  | 26/07/2024 |  |  | CJR | 0 |  |  | 2024-06-30 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-07-26 | 2050-01-01 | -9213
353 | 354 | ATL-BDD-CC-DW-1910 | CUADRO DE COMUNICACIONES SCADA | EQUIPMENT | BESS | EQUIPMENT | SCADA and PPC |  | 30/07/2024 |  |  |  | 30/08/2024 |  |  | CJR | 16 |  |  | 2024-07-30 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-08-30 | 2050-01-01 | -9213
347 | 348 | ATL-BDD-CC-PR-1902 | PROCEDIMIENTO DE PRUEBAS SIT | EQUIPMENT | BESS | EQUIPMENT | SCADA and PPC |  | 25/07/2024 |  |  |  | 23/08/2024 |  |  | CJR | 18 |  |  | 2024-07-25 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-08-23 | 2050-01-01 | -9213
340 | 341 | ATL-BDD-ELE-DW-1934 | PLANTA GENERAL SECCIONAMIENTO 4 - DETECCION DE INCENDIOS | EQUIPMENT | BESS | EQUIPMENT | Switching Building |  | 01/08/2024 |  |  |  | 30/08/2024 |  |  | CJR | 18 |  |  | 2024-08-01 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-08-30 | 2050-01-01 | -9213
339 | 340 | ATL-BDD-ELE-DW-1933 | PLANTA GENERAL SECCIONAMIENTO 3 - DETECCION DE INCENDIOS | EQUIPMENT | BESS | EQUIPMENT | Switching Building |  | 01/08/2024 |  |  |  | 30/08/2024 |  |  | CJR | 18 |  |  | 2024-08-01 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-08-30 | 2050-01-01 | -9213
116 | 117 | ATL-BDD-ELE-ET-1430 | ESPECIFICACIÓN PCYM Y COMUNICACIÓN | EQUIPMENT | BESS | EQUIPMENT | Communications |  | 01/07/2024 |  |  |  | 29/07/2024 |  |  | CJR | 1 |  |  | 2024-07-01 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-07-29 | 2050-01-01 | -9213
176 | 177 | ATL-BDD-CIV-DW-1801 | O&M. FUNDACIONES. PLANO & DETALLES | CIVIL | BESS | CIVIL | O&M Building |  | 09/08/2024 |  |  |  | 06/09/2024 |  |  | CJR | 15 |  |  | 2024-08-09 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-09-06 | 2050-01-01 | -9213
178 | 179 | ATL-BDD-CIV-DW-1803 | O&M. ESTRUCTURA METALICA. PLANO & DETALLES | CIVIL | BESS | CIVIL | O&M Building |  | 09/08/2024 |  |  |  | 06/09/2024 |  |  | CJR | 15 |  |  | 2024-08-09 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-09-06 | 2050-01-01 | -9213
179 | 180 | ATL-BDD-CIV-MC-1804 | O&M. ESTRUCTURA METALICA. MC | CIVIL | BESS | CIVIL | O&M Building |  | 09/08/2024 |  |  |  | 06/09/2024 |  |  | CJR | 15 |  |  | 2024-08-09 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-09-06 | 2050-01-01 | -9213
180 | 181 | ATL-BDD-ELE-DW-1805 | O&M. ALUMBRADO. PLANO & DETALLES | ELECTROMECHANICAL | BESS | ELECTROMECHANICAL | O&M Building |  | 09/08/2024 |  |  |  | 06/09/2024 |  |  | CJR | 15 |  |  | 2024-08-09 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-09-06 | 2050-01-01 | -9213
181 | 182 | ATL-BDD-ELE-MC-1806 | O&M.ALUMBRADO. MC | ELECTRICAL | BESS | ELECTRICAL | O&M Building |  | 09/08/2024 |  |  |  | 06/09/2024 |  |  | CJR | 15 |  |  | 2024-08-09 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-09-06 | 2050-01-01 | -9213
338 | 339 | ATL-BDD-ELE-DW-1932 | PLANTA GENERAL SECCIONAMIENTO 2 - DETECCION DE INCENDIOS | EQUIPMENT | BESS | EQUIPMENT | Switching Building |  | 01/08/2024 |  |  |  | 30/08/2024 |  |  | CJR | 18 |  |  | 2024-08-01 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-08-30 | 2050-01-01 | -9213
183 | 184 | ATL-BDD-CIV-DW-1821 | WHAREHOUSE. FUNDACIONES. PLANO & DETALLES | CIVIL | BESS | CIVIL | Other Buildings |  | 09/08/2024 |  |  |  | 06/09/2024 |  |  | CJR | 15 |  |  | 2024-08-09 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-09-06 | 2050-01-01 | -9213
184 | 185 | ATL-BDD-CIV-MC-1822 | WHAREHOUSE. ESTRUCTURA. FUNDACIONES. MC | CIVIL | BESS | CIVIL | Other Buildings |  | 09/08/2024 |  |  |  | 06/09/2024 |  |  | CJR | 15 |  |  | 2024-08-09 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-09-06 | 2050-01-01 | -9213
185 | 186 | ATL-BDD-CIV-DW-1823 | WHAREHOUSE. ESTRUCTURA METALICA. PLANO & DETALLES | CIVIL | BESS | CIVIL | Other Buildings |  | 09/08/2024 |  |  |  | 06/09/2024 |  |  | CJR | 15 |  |  | 2024-08-09 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-09-06 | 2050-01-01 | -9213
186 | 187 | ATL-BDD-CIV-MC-1824 | WHAREHOUSE. ESTRUCTURA METALICA. MC | CIVIL | BESS | CIVIL | Other Buildings |  | 09/08/2024 |  |  |  | 06/09/2024 |  |  | CJR | 15 |  |  | 2024-08-09 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-09-06 | 2050-01-01 | -9213
187 | 188 | ATL-BDD-ELE-DW-1825 | WHAREHOUSE. ALUMBRADO. PLANO & DETALLES | ELECTROMECHANICAL | BESS | ELECTROMECHANICAL | Other Buildings |  | 09/08/2024 |  |  |  | 06/09/2024 |  |  | CJR | 15 |  |  | 2024-08-09 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-09-06 | 2050-01-01 | -9213
188 | 189 | ATL-BDD-ELE-MC-1826 | WHAREHOUSE.ALUMBRADO. MC | ELECTRICAL | BESS | ELECTRICAL | Other Buildings |  | 09/08/2024 |  |  |  | 06/09/2024 |  |  | CJR | 15 |  |  | 2024-08-09 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-09-06 | 2050-01-01 | -9213
337 | 338 | ATL-BDD-ELE-DW-1931 | PLANTA GENERAL SECCIONAMIENTO 1 - DETECCION DE INCENDIOS | EQUIPMENT | BESS | EQUIPMENT | Switching Building |  | 01/08/2024 |  |  |  | 30/08/2024 |  |  | CJR | 18 |  |  | 2024-08-01 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-08-30 | 2050-01-01 | -9213
326 | 327 | ATL-BDD-ELE-ES-1510 | ESTUDIO DE AJUSTE DE PROTECCIONES CELDAS MT | EQUIPMENT | BESS | EQUIPMENT | MV Equipment |  | 09/08/2024 |  |  |  | 13/09/2024 |  |  | CJR | 18 |  |  | 2024-08-09 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-09-13 | 2050-01-01 | -9213
454 | 456 | ATL-BDD-ELE-BT-2007 | Prensaestopas | EQUIPMENT | BESS | EQUIPMENT | Low Voltage AC |  | 08/10/2024 |  |  |  | 12/10/2024 |  |  | CJR | 35 |  |  | 2024-10-08 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-10-12 | 2050-01-01 | -9213
177 | 178 | ATL-BDD-CIV-MC-1802 | O&M. ESTRUCTURA. FUNDACIONES. MC | CIVIL | BESS | CIVIL | O&M Building |  | 09/08/2024 |  |  |  | 06/09/2024 |  |  | CJR | 15 |  |  | 2024-08-09 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-09-06 | 2050-01-01 | -9213
375 | 376 | ALT-BDD-ELE-BT-1965 | CELDAS MT 36 KV | EQUIPMENT | BESS | EQUIPMENT | MV Equipment |  | 18/08/2024 |  |  |  | 28/08/2024 |  |  | CJR | 25 |  |  | 2024-08-18 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-08-28 | 2050-01-01 | -9213
376 | 377 | ALT-BDD-ELE-BT-1967 | TERMINALES MT | EQUIPMENT | BESS | EQUIPMENT | Medium Voltage |  | 18/08/2024 |  |  |  | 28/08/2024 |  |  | CJR | 25 |  |  | 2024-08-18 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-08-28 | 2050-01-01 | -9213
105 | 106 | ATL-BDD-ELE-MC-1408 | DIMENSIONAMIENTO DE TRAFO SSAA/BESS | ELECTRICAL | BESS | ELECTRICAL | Auxiliary System |  | 29/07/2024 |  |  |  | 28/08/2024 |  |  | CJR | 18 |  |  | 2024-07-29 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-08-28 | 2050-01-01 | -9213
453 | 455 | ATL-BDD-ELE-ET-2006 | Marcador de cables WMTB HF (55 x 15) R | EQUIPMENT | BESS | EQUIPMENT | Low Voltage AC |  | 08/10/2024 |  |  |  | 12/10/2024 |  |  | CJR | 35 |  |  | 2024-10-08 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-10-12 | 2050-01-01 | -9213
452 | 454 | ATL-BDD-ELE-BT-2005 | Entubado termorretractil WMS 9_5 | EQUIPMENT | BESS | EQUIPMENT | Low Voltage AC |  | 08/10/2024 |  |  |  | 12/10/2024 |  |  | CJR | 35 |  |  | 2024-10-08 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-10-12 | 2050-01-01 | -9213
451 | 453 | ATL-BDD-ELE-ET-2004 | Entubado termorRetractil WMS 6_4 | EQUIPMENT | BESS | EQUIPMENT | Low Voltage AC |  | 08/10/2024 |  |  |  | 12/10/2024 |  |  | CJR | 35 |  |  | 2024-10-08 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-10-12 | 2050-01-01 | -9213
450 | 452 | ATL-BDD-ELE-BT-2003 | Terminacion de Exterior con terminales de tornilleria fusible | EQUIPMENT | BESS | EQUIPMENT | Medium Voltage |  | 08/10/2024 |  |  |  | 12/10/2024 |  |  | CJR | 35 |  |  | 2024-10-08 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-10-12 | 2050-01-01 | -9213
446 | 448 | ATL-BDD-ELE-LS-1442 | ARCHIVOS CID RELÉS DE PROTECCIÓN | EQUIPMENT | BESS | EQUIPMENT | P&C System |  | 14/11/2024 |  |  |  | 04/12/2024 |  |  | CJR | 34 |  |  | 2024-11-14 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-12-04 | 2050-01-01 | -9213
445 | 447 | ATL-BDD-ELE-LS-1441 | LISTA DE SEÑALES A SCADA | EQUIPMENT | BESS | EQUIPMENT | P&C System |  | 07/10/2024 |  |  |  | 27/10/2024 |  |  | CJR | 34 |  |  | 2024-10-07 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-10-27 | 2050-01-01 | -9213
443 | 444 | ATL-BDD-ELE-MC-1675 | NCS - MEMORIA HVAC | ELECTRICAL | BESS | ELECTRICAL | Switching Building |  | 03/10/2024 |  |  |  | 31/10/2024 |  |  | CJR | 34 |  |  | 2024-10-03 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-10-31 | 2050-01-01 | -9213
442 | 443 | ATL-BDD-CIV-MC-1674 | NCS - MEMORIA ESTRUCTURAL | CIVIL | BESS | CIVIL | Switching Building |  | 01/10/2024 |  |  |  | 28/10/2024 |  |  | CJR | 34 |  |  | 2024-10-01 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-10-28 | 2050-01-01 | -9213
440 | 441 | ATL-BDD-ELE-DW-1672 | NCS - PLANILLA DE CONEXIONADO | ELECTROMECHANICAL | BESS | ELECTROMECHANICAL | Switching Building |  | 01/11/2024 |  |  |  | 29/11/2024 |  |  | CJR | 34 |  |  | 2024-11-01 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-11-29 | 2050-01-01 | -9213
439 | 440 | ATL-BDD-ELE-MC-1671 | NCS - MEMORIA DE CALCULO SISTEMA CONTRA INCENDIOS | EQUIPMENT | BESS | EQUIPMENT | Switching Building |  | 03/10/2024 |  |  |  | 31/10/2024 |  |  | CJR | 34 |  |  | 2024-10-03 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-10-31 | 2050-01-01 | -9213
438 | 439 | ATL-BDD-ELE-DW-1670 | NCS - PLANTA DISPOSICION DETECCION Y EXTINCION DE INCENDIOS | EQUIPMENT | BESS | EQUIPMENT | Switching Building |  | 25/09/2024 |  |  |  | 25/10/2024 |  |  | CJR | 34 |  |  | 2024-09-25 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-10-25 | 2050-01-01 | -9213
437 | 438 | ATL-BDD-ELE-DW-1669 | NCS - DISPOSICION DE CANALIZACIONES | ELECTROMECHANICAL | BESS | ELECTROMECHANICAL | Switching Building |  | 25/09/2024 |  |  |  | 25/10/2024 |  |  | CJR | 34 |  |  | 2024-09-25 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-10-25 | 2050-01-01 | -9213
28 | 29 | ATL-BDD-23134-QAC-LS-01 | Quality Book Tracker | EQUIPMENT | BESS | EQUIPMENT | Rectifier / Battery |  | 13/05/2024 |  |  |  | 10/06/2024 |  |  | SUNGROW | 0 |  |  | 2024-05-13 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-06-10 | 2050-01-01 | -9213
436 | 437 | ATL-BDD-ELE-DW-1668 | NCS - DIAGRAMAS ELEMENTAL CA Y EQUIPOS | ELECTROMECHANICAL | BESS | ELECTROMECHANICAL | Switching Building |  | 01/11/2024 |  |  |  | 29/11/2024 |  |  | CJR | 34 |  |  | 2024-11-01 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-11-29 | 2050-01-01 | -9213
435 | 436 | ATL-BDD-CIV-DW-1664 | NCS - DISPOSICION DE CANALIZACIONES - PLANTA | ELECTRICAL | BESS | ELECTROMECHANICAL | Switching Building |  | 01/11/2024 |  |  |  | 29/11/2024 |  |  | CJR | 34 |  |  | 2024-11-01 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-11-29 | 2050-01-01 | -9213
433 | 434 | ATL-BDD-ELE-DW-1662 | NCS - PLANTA DE DISPOSICION DE ALUMBRADO Y ENCHUFES | ELECTROMECHANICAL | BESS | ELECTROMECHANICAL | Switching Building |  | 03/10/2024 |  |  |  | 31/10/2024 |  |  | CJR | 34 |  |  | 2024-10-03 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-10-31 | 2050-01-01 | -9213
431 | 432 | ATL-BDD-CC-DW-1647 | CS - FUNDACION GENERADOR (PLANO) | EQUIPMENT | BESS | EQUIPMENT | Auxiliary System |  | 06/09/2024 |  |  |  | 04/10/2024 |  |  | CJR | 34 |  |  | 2024-09-06 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-10-04 | 2050-01-01 | -9213
101 | 102 | ATL-BDD-ELE-DW-1404 | DETALLE DE ZANJAS / BANDEJAS | ELECTROMECHANICAL | BESS | ELECTROMECHANICAL | Ducts/channels/cable trays |  | 31/07/2024 |  |  |  | 30/08/2024 |  |  | CJR | 18 |  |  | 2024-07-31 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-08-30 | 2050-01-01 | -9213
379 | 380 | ALT-BDD-ELE-BT-1970 | TRANSFORMADOR ENCAPSULADO EN RESINA 33KV_400KVA | EQUIPMENT | BESS | EQUIPMENT | P&C System |  | 18/08/2024 |  |  |  | 28/08/2024 |  |  | CJR | 25 |  |  | 2024-08-18 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-08-28 | 2050-01-01 | -9213
419 | 420 | ATL-BDD-ELE-1990 | BANDEJAS PORTACABLES DE ACERO GALBANIZADO | EQUIPMENT | BESS | EQUIPMENT | Ducts/channels/cable trays |  | 23/09/2024 |  |  |  | 30/09/2024 |  |  | CJR | 32 |  |  | 2024-09-23 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-09-30 | 2050-01-01 | -9213
420 | 421 | ATL-BDD-MEC-BT-1991 | TUBERIA CORRUGADA 2" | EQUIPMENT | BESS | EQUIPMENT | Ducts/channels/cable trays |  | 23/09/2024 |  |  |  | 30/09/2024 |  |  | CJR | 32 |  |  | 2024-09-23 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-09-30 | 2050-01-01 | -9213
81 | 82 | ATL-BDD-CIV-MC-1109 | ESTRUCTURA PARA-RAYOS. MEMORIA DE CÁLCULO | CIVIL | BESS | CIVIL | Minor Structures |  | 31/07/2024 |  |  |  | 30/08/2024 |  |  | CJR | 18 |  |  | 2024-07-31 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-08-30 | 2050-01-01 | -9213
421 | 422 | ATL-BDD-MEC-BT-1992 | TUBERIA CORRUGADA 4" | EQUIPMENT | BESS | EQUIPMENT | Ducts/channels/cable trays |  | 23/09/2024 |  |  |  | 30/09/2024 |  |  | CJR | 32 |  |  | 2024-09-23 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-09-30 | 2050-01-01 | -9213
294 | 295 | ATL-BDD-ELE-MC-1617 | MEMORIA CALCULO SISTEMA CONTRA INCENDIOS | EQUIPMENT | BESS | EQUIPMENT | Switching Building |  | 30/06/2024 |  | 23/07/2024 |  | 25/07/2024 |  |  | CJR | 34 |  |  | 2024-06-30 | 2050-01-01 | 2024-07-23 | 2050-01-01 | 2024-07-25 | 2050-01-01 | -9213
422 | 423 | ATL-BDD-CIV-BT-2003 | COLMA FIX - 32 | EQUIPMENT | BESS | EQUIPMENT | Ducts/channels/cable trays |  | 24/09/2024 |  |  |  | 30/09/2024 |  |  | CJR | 32 |  |  | 2024-09-24 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-09-30 | 2050-01-01 | -9213
424 | 425 | ATL-BDD-CIV-BT-2005 | SIKAFLEX - 1A | EQUIPMENT | BESS | EQUIPMENT | Ducts/channels/cable trays |  | 24/09/2024 |  |  |  | 30/09/2024 |  |  | CJR | 32 |  |  | 2024-09-24 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-09-30 | 2050-01-01 | -9213
70 | 71 | ATL-BDD-GEN-LS-1010 | LISTA DE MATERIALES CIVILES | CIVIL | BESS | CIVIL | General |  | 29/07/2024 |  |  |  | 28/08/2024 |  |  | CJR | 18 |  |  | 2024-07-29 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-08-28 | 2050-01-01 | -9213
425 | 426 | ATL-BDD-CIV-BT-2006 | SIKA ANTISOL | EQUIPMENT | BESS | EQUIPMENT | Ducts/channels/cable trays |  | 24/09/2024 |  |  |  | 30/09/2024 |  |  | CJR | 32 |  |  | 2024-09-24 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-09-30 | 2050-01-01 | -9213
53 | 54 | ATL-BDD-23134-QAC-CE-12 | Liquid Coolant - MSDS | EQUIPMENT | BESS | EQUIPMENT | Rectifier / Battery |  | 13/05/2024 |  |  |  | 10/06/2024 |  |  | SUNGROW | 0 |  |  | 2024-05-13 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-06-10 | 2050-01-01 | -9213
427 | 428 | ATL-BDD-MEC-IN-1963 | Plano Dimensional de TTR 100KVA | EQUIPMENT | BESS | EQUIPMENT | P&C System |  | 16/08/2024 |  |  |  | 05/09/2024 |  |  | CJR | 33 |  |  | 2024-08-16 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-09-05 | 2050-01-01 | -9213
430 | 431 | ATL-BDD-CC-DW-1646 | CS - FUNDACION GENERADOR (MC) | EQUIPMENT | BESS | EQUIPMENT | Auxiliary System |  | 06/09/2024 |  |  |  | 04/10/2024 |  |  | CJR | 34 |  |  | 2024-09-06 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-10-04 | 2050-01-01 | -9213
423 | 424 | ATL-BDD-CIV-BT-2004 | IGOL DENSO | EQUIPMENT | BESS | EQUIPMENT | Ducts/channels/cable trays |  | 24/09/2024 |  |  |  | 30/09/2024 |  |  | CJR | 32 |  |  | 2024-09-24 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-09-30 | 2050-01-01 | -9213
289 | 290 | ATL-BDD-GEN-ES-1006 | RESISTIVIIDAD | ELECTRICAL | BESS | ELECTRICAL | Studies |  | 27/05/2024 |  |  |  | 16/06/2024 |  |  | CJR | 6 |  |  | 2024-05-27 | 2050-01-01 | 2050-01-01 | 2050-01-01 | 2024-06-16 | 2050-01-01 | -9213
455 | 457 | ATL-BDD-CIV-DW-1676 | NCS - CALADOS DE PISO | CIVIL | BESS | CIVIL | Switching Building | 0A | 01/10/2024 |  | 11/10/2024 | 11/10/2024 | 28/10/2024 |  |  | CJR | 36 | For Analysis |  | 2024-10-01 | 2050-01-01 | 2024-10-11 | 2024-10-11 | 2024-10-28 | 2050-01-01 | 0
302 | 303 | ATL-BDD-CC-DW-1641 | CS - ARQUITECTURA DE COMUNICACIONES Y SCADA (BESS) | EQUIPMENT | BESS | EQUIPMENT | Switching Building | 0D | 14/06/2024 |  | 24/06/2024 | 10/10/2024 | 04/07/2024 |  |  | CJR | 10 | For Analysis |  | 2024-06-14 | 2050-01-01 | 2024-06-24 | 2024-10-10 | 2024-07-04 | 2050-01-01 | 1
441 | 442 | ATL-BDD-CIV-DW-1673 | NCS - DISPOSICION DE APOYOS Y ANCALJES | EQUIPMENT | BESS | EQUIPMENT | Switching Building | 0A | 02/10/2024 |  | 10/10/2024 | 10/10/2024 | 29/10/2024 |  |  | CJR | 34 | For Analysis |  | 2024-10-02 | 2050-01-01 | 2024-10-10 | 2024-10-10 | 2024-10-29 | 2050-01-01 | 1
432 | 433 | ATL-BDD-CIV-DW-1661 | NCS - ARQUITECTURA PLANTA Y PERFILES | CIVIL | BESS | CIVIL | Switching Building | 0A | 03/10/2024 |  | 10/10/2024 | 10/10/2024 | 31/10/2024 |  |  | CJR | 34 | For Analysis |  | 2024-10-03 | 2050-01-01 | 2024-10-10 | 2024-10-10 | 2024-10-31 | 2050-01-01 | 1
182 | 183 | ATL-BDD-CIV-DW-1820 | WHAREHOUSE. ARQUITECTURA. LAYOUT (84 m2) | CIVIL | BESS | CIVIL | Other Buildings | 0A | 09/08/2024 |  | 10/10/2024 | 10/10/2024 | 06/09/2024 |  |  | CJR | 15 | For Analysis |  | 2024-08-09 | 2050-01-01 | 2024-10-10 | 2024-10-10 | 2024-09-06 | 2050-01-01 | 1
320 | 321 | ATL-BDD-23134-CYC-LS-02 | Cyber Assets List | EQUIPMENT | BESS | EQUIPMENT | Rectifier / Battery | 0C | 27/06/2024 |  | 03/07/2024 | 10/10/2024 | 11/07/2024 |  |  | SUNGROW | 13 | For Analysis |  | 2024-06-27 | 2050-01-01 | 2024-07-03 | 2024-10-10 | 2024-07-11 | 2050-01-01 | 1
175 | 176 | ATL-BDD-CIV-DW-1800 | O&M. ARQUITECTURA. LAYOUT (84 m2) | CIVIL | BESS | CIVIL | O&M Building | 0A | 09/08/2024 |  | 10/10/2024 | 10/10/2024 | 06/09/2024 |  |  | CJR | 15 | For Analysis |  | 2024-08-09 | 2050-01-01 | 2024-10-10 | 2024-10-10 | 2024-09-06 | 2050-01-01 | 1
172 | 173 | ATL-BDD-GEN-DW-1700 | VALLADO. DETALLES | CIVIL | BESS | CIVIL | Security Fence | 0A | 15/08/2024 |  | 10/10/2024 | 10/10/2024 | 13/09/2024 |  |  | CJR | 18 | For Analysis |  | 2024-08-15 | 2050-01-01 | 2024-10-10 | 2024-10-10 | 2024-09-13 | 2050-01-01 | 1
352 | 353 | ATL-BDD-CC-LS-1909 | LISTADO DE PROTOCOLOS (IP) | EQUIPMENT | BESS | EQUIPMENT | SCADA and PPC | 0B | 19/07/2024 |  | 02/08/2024 | 10/10/2024 | 16/08/2024 |  |  | CJR | 16 | For Analysis |  | 2024-07-19 | 2050-01-01 | 2024-08-02 | 2024-10-10 | 2024-08-16 | 2050-01-01 | 1
434 | 435 | ATL-BDD-ELE-DW-1663 | NCS - MALLA PUESTA A TIERRA | ELECTROMECHANICAL | BESS | ELECTROMECHANICAL | Switching Building | 0A | 02/10/2024 |  | 09/10/2024 | 09/10/2024 | 29/10/2024 |  |  | CJR | 34 | For Analysis |  | 2024-10-02 | 2050-01-01 | 2024-10-09 | 2024-10-09 | 2024-10-29 | 2050-01-01 | 2
429 | 430 | ATL-BDD-ELE-DW-1440 | SE - DISPOSICION DE CANALIZACIONES BAJA TENSION Y COMUNICACIONES - DETALLES | ELECTROMECHANICAL | BESS | ELECTROMECHANICAL | Ducts/channels/cable trays | 0A | 01/11/2024 |  | 09/10/2024 | 09/10/2024 | 29/11/2024 |  |  | CJR | 34 | For Analysis |  | 2024-11-01 | 2050-01-01 | 2024-10-09 | 2024-10-09 | 2024-11-29 | 2050-01-01 | 2
428 | 429 | ATL-BDD-ELE-DW-1439 | SE - DISPOSICION DE CANALIZACIONES BAJA TENSION Y COMUNICACIONES - PLANTA | ELECTROMECHANICAL | BESS | ELECTROMECHANICAL | Ducts/channels/cable trays | 0A | 01/11/2024 |  | 09/10/2024 | 09/10/2024 | 29/11/2024 |  |  | CJR | 34 | For Analysis |  | 2024-11-01 | 2050-01-01 | 2024-10-09 | 2024-10-09 | 2024-11-29 | 2050-01-01 | 2
360 | 361 | ATL-BDD-ELE-DW-1523 | NCS SECONDAR DIAGRAM CELDAS CS | EQUIPMENT | BESS | EQUIPMENT | MV Equipment | 0C | 16/08/2024 |  | 27/08/2024 | 09/10/2024 | 13/09/2024 |  |  | CJR | 20 | For Analysis |  | 2024-08-16 | 2050-01-01 | 2024-08-27 | 2024-10-09 | 2024-09-13 | 2050-01-01 | 2
342 | 343 | ATL-BDD-ELE-DW-1936 | DETALLES - DETECCION DE INCENDIOS | EQUIPMENT | BESS | EQUIPMENT | Switching Building | 0B | 01/08/2024 |  | 26/08/2024 | 08/10/2024 | 30/08/2024 |  |  | CJR | 18 | For Analysis |  | 2024-08-01 | 2050-01-01 | 2024-08-26 | 2024-10-08 | 2024-08-30 | 2050-01-01 | 3
336 | 337 | ATL-BDD-ELE-DW-1930 | PLANTA GENERAL - DETECCION DE INCENDIOS | EQUIPMENT | BESS | EQUIPMENT | Switching Building | 0B | 01/08/2024 |  | 26/08/2024 | 08/10/2024 | 30/08/2024 |  |  | CJR | 18 | For Analysis |  | 2024-08-01 | 2050-01-01 | 2024-08-26 | 2024-10-08 | 2024-08-30 | 2050-01-01 | 3
343 | 344 | ATL-BDD-ELE-ET-1937 | PCI - ESPECIFICACIONES TECNICAS | EQUIPMENT | BESS | EQUIPMENT | Switching Building | 0B | 01/08/2024 |  | 02/09/2024 | 08/10/2024 | 30/08/2024 |  |  | CJR | 18 | For Analysis |  | 2024-08-01 | 2050-01-01 | 2024-09-02 | 2024-10-08 | 2024-08-30 | 2050-01-01 | 3
401 | 402 | ATL-BDD-ELE-MC-1939 | MEMORIA DE DETECCION INCENDIO | EQUIPMENT | BESS | EQUIPMENT | Switching Building | 0A | 05/09/2024 |  | 08/10/2024 | 08/10/2024 | 25/09/2024 |  |  | CJR | 29 | For Analysis |  | 2024-09-05 | 2050-01-01 | 2024-10-08 | 2024-10-08 | 2024-09-25 | 2050-01-01 | 3
301 | 302 | ATL-BDD-CC-DW-1642 | CS - ARQUITECTURA DE COMUNICACIONES Y SCADA (SCI) | EQUIPMENT | BESS | EQUIPMENT | Switching Building | 0B | 28/06/2024 |  | 26/08/2024 | 08/10/2024 | 26/07/2024 |  |  | CJR | 10 | For Analysis |  | 2024-06-28 | 2050-01-01 | 2024-08-26 | 2024-10-08 | 2024-07-26 | 2050-01-01 | 3
426 | 427 | ATL-BDD-ELE-DW-1667 | NCS - CANALIZACIÓN FUERZA_CONTROL Y COMUNICACIÓN CELDAS | ELECTROMECHANICAL | BESS | ELECTROMECHANICAL | Switching Building | 0A | 25/09/2024 |  | 08/10/2024 | 08/10/2024 | 15/10/2024 |  |  | CJR | 32 | For Analysis |  | 2024-09-25 | 2050-01-01 | 2024-10-08 | 2024-10-08 | 2024-10-15 | 2050-01-01 | 3
374 | 375 | ATL-BDD-ELE-DW-1660 | NCS - DISPOSICION DE EQUIPOS | ELECTROMECHANICAL | BESS | ELECTROMECHANICAL | Switching Building | 0B | 14/08/2024 |  | 14/08/2024 | 08/10/2024 | 10/09/2024 |  |  | CJR | 23 | For Analysis |  | 2024-08-14 | 2050-01-01 | 2024-08-14 | 2024-10-08 | 2024-09-10 | 2050-01-01 | 3
341 | 342 | ATL-BDD-ELE-DW-1935 | DIAGRAMA DE CONEXIONADO | EQUIPMENT | BESS | EQUIPMENT | Switching Building | 0B | 01/08/2024 |  | 26/08/2024 | 08/10/2024 | 30/08/2024 |  |  | CJR | 18 | For Analysis |  | 2024-08-01 | 2050-01-01 | 2024-08-26 | 2024-10-08 | 2024-08-30 | 2050-01-01 | 3
106 | 107 | ATL-BDD-ELE-DW-1409 | DETALLES CABLEADO Y CONEXIONADO MT | ELECTROMECHANICAL | BESS | ELECTROMECHANICAL | Medium Voltage | 0B | 24/07/2024 |  | 01/08/2024 | 07/10/2024 | 23/08/2024 |  |  | CJR | 18 | For Analysis |  | 2024-07-24 | 2050-01-01 | 2024-08-01 | 2024-10-07 | 2024-08-23 | 2050-01-01 | 4
323 | 324 | ATL-BDD-ELE-ES-1427 | CAPACIDAD MECANICA DE BARRA TRAFO SE | ELECTRICAL | BESS | ELECTRICAL | Auxiliary System | 1A | 05/07/2024 |  | 12/07/2024 | 07/10/2024 | 02/08/2024 |  |  | CJR | 15 | For Analysis |  | 2024-07-05 | 2050-01-01 | 2024-07-12 | 2024-10-07 | 2024-08-02 | 2050-01-01 | 4
96 | 97 | ATL-BDD-ELE-DW-1403 | PLANO DE CANALIZACIONES BT | ELECTROMECHANICAL | BESS | ELECTROMECHANICAL | Ducts/channels/cable trays | 0D | 29/07/2024 |  | 09/07/2024 | 04/10/2024 | 26/08/2024 |  |  | CJR | 0 | For Analysis |  | 2024-07-29 | 2050-01-01 | 2024-07-09 | 2024-10-04 | 2024-08-26 | 2050-01-01 | 7
108 | 109 | ATL-BDD-ELE-DW-1411 | DETALLES CABLEADO Y CONEXIONADO BT SSAA | ELECTROMECHANICAL | BESS | ELECTROMECHANICAL | Auxiliary System | 0A | 29/07/2024 |  | 04/10/2024 | 04/10/2024 | 28/08/2024 |  |  | CJR | 18 | For Analysis |  | 2024-07-29 | 2050-01-01 | 2024-10-04 | 2024-10-04 | 2024-08-28 | 2050-01-01 | 7
20 | 21 | ATL-BDD-23134-CIV-MC-02 | Liquid Cooling ESS - Seismic Analysis | EQUIPMENT | BESS | EQUIPMENT | Rectifier / Battery | 00 | 28/04/2024 |  | 06/05/2024 | 03/10/2024 | 28/05/2024 |  | 24/06/2024 | SUNGROW | 0 | For revision |  | 2024-04-28 | 2050-01-01 | 2024-05-06 | 2024-10-03 | 2024-05-28 | 2050-01-01 | 8
66 | 67 | ATL-BDD-GEN-DW-1003 | TOPOGRAFIA | CIVIL | BESS | CIVIL | Topographic Survey | 0C | 16/04/2024 |  | 29/04/2024 | 03/10/2024 | 14/05/2024 |  |  | CJR | 0 | For Analysis |  | 2024-04-16 | 2050-01-01 | 2024-04-29 | 2024-10-03 | 2024-05-14 | 2050-01-01 | 8
161 | 162 | ATL-BDD-ELE-DW-1618 | CS - PLANILLA DE CONEXIONADO | ELECTROMECHANICAL | BESS | ELECTROMECHANICAL | Switching Building | 0B | 30/06/2024 |  | 29/08/2024 | 03/10/2024 | 26/07/2024 |  |  | CJR | 0 | For Analysis |  | 2024-06-30 | 2050-01-01 | 2024-08-29 | 2024-10-03 | 2024-07-26 | 2050-01-01 | 8
362 | 363 | ATL-BDD-ELE-DW-1525 | NCS DIAGRAMA DE LOGICA Y ENCLAVAMIENTOS | ELECTRICAL | BESS | ELECTRICAL | P&C System | 0A | 25/10/2024 |  | 03/10/2024 | 03/10/2024 | 22/11/2024 |  |  | CJR | 20 | For Analysis |  | 2024-10-25 | 2050-01-01 | 2024-10-03 | 2024-10-03 | 2024-11-22 | 2050-01-01 | 8
88 | 89 | ATL-BDD-ELE-DW-1300 | DIAGRAMA UNILINEAL FUNCIONAL | ELECTRICAL | BESS | ELECTRICAL | General | 0C | 30/04/2024 |  | 13/06/2024 | 02/10/2024 | 28/05/2024 |  |  | CJR | 0 | For Analysis |  | 2024-04-30 | 2050-01-01 | 2024-06-13 | 2024-10-02 | 2024-05-28 | 2050-01-01 | 9
160 | 161 | ATL-BDD-ELE-MC-1616 | CS - MEMORIA CALCULO ILUMINACION | ELECTRICAL | BESS | ELECTRICAL | Switching Building | 0C | 30/06/2024 |  | 23/07/2024 | 02/10/2024 | 26/07/2024 |  |  | CJR | 0 | For Analysis |  | 2024-06-30 | 2050-01-01 | 2024-07-23 | 2024-10-02 | 2024-07-26 | 2050-01-01 | 9
147 | 148 | ATL-BDD-ELE-DW-1602 | CS - PLANTA DE DISPOSICION DE ALUMBRADO Y ENCHUFES | ELECTROMECHANICAL | BESS | ELECTROMECHANICAL | Switching Building | 0C | 30/06/2024 |  | 02/07/2024 | 02/10/2024 | 26/07/2024 |  |  | CJR | 0 | For Analysis |  | 2024-06-30 | 2050-01-01 | 2024-07-02 | 2024-10-02 | 2024-07-26 | 2050-01-01 | 9
400 | 401 | ATL-BDD-ELE-DW-1632 | CS - TABLERO DE TRANSFERENCIA AUTOMATICA GRUPO ELECTRÓGENO | ELECTRICAL | BESS | ELECTRICAL | Auxiliary System | 0B | 18/09/2024 |  | 10/09/2024 | 30/09/2024 | 11/10/2024 |  |  | CJR | 29 | For Analysis |  | 2024-09-18 | 2050-01-01 | 2024-09-10 | 2024-09-30 | 2024-10-11 | 2050-01-01 | 11
415 | 416 | ATL-BDD-ELE-DW-1681 | NCS - DISPOSICIÓN DE CANALIZACIONES MT - SECCION Y DETALLES | ELECTROMECHANICAL | BESS | ELECTROMECHANICAL | Switching Building | 0B | 12/09/2024 |  | 13/09/2024 | 27/09/2024 | 11/10/2024 |  |  | CJR | 30 | For Analysis |  | 2024-09-12 | 2050-01-01 | 2024-09-13 | 2024-09-27 | 2024-10-11 | 2050-01-01 | 14
414 | 415 | ATL-BDD-ELE-DW-1680 | NCS - DISPOSICIÓN DE CANALIZACIONES MT - PLANTA | ELECTROMECHANICAL | BESS | ELECTROMECHANICAL | Switching Building | 0B | 12/09/2024 |  | 13/09/2024 | 27/09/2024 | 11/10/2024 |  |  | CJR | 30 | For Analysis |  | 2024-09-12 | 2050-01-01 | 2024-09-13 | 2024-09-27 | 2024-10-11 | 2050-01-01 | 14
325 | 326 | ATL-BDD-CC-DW-1429 | COMUNICACION Y SEÑALES A SE | EQUIPMENT | BESS | EQUIPMENT | General | 0A | 17/07/2024 |  | 27/09/2024 | 27/09/2024 | 16/08/2024 |  |  | CJR | 15 | For Analysis |  | 2024-07-17 | 2050-01-01 | 2024-09-27 | 2024-09-27 | 2024-08-16 | 2050-01-01 | 14
151 | 152 | ATL-BDD-ELE-DW-1606 | CS - CANALIZACIÓN FUERZA_CONTROL Y COMUNICACIÓN CELDAS | ELECTROMECHANICAL | BESS | ELECTROMECHANICAL | Switching Building | 0B | 30/06/2024 |  | 19/08/2024 | 26/09/2024 | 26/07/2024 |  |  | CJR | 0 | For Analysis |  | 2024-06-30 | 2050-01-01 | 2024-08-19 | 2024-09-26 | 2024-07-26 | 2050-01-01 | 15
328 | 329 | ATL-BDD-CIV-DW-1644 | CS - FUNDACION TRAFO SSAA (PLANO) | ELECTRICAL | BESS | ELECTRICAL | Auxiliary System | 0A | 08/08/2024 |  | 24/09/2024 | 24/09/2024 | 06/09/2024 |  |  | CJR | 15 | Non-compliant |  | 2024-08-08 | 2050-01-01 | 2024-09-24 | 2024-09-24 | 2024-09-06 | 2050-01-01 | 17
398 | 399 | ALT-BDD-ELE-BT-1989 | TERMINACIONES PFISTER S3 | EQUIPMENT | BESS | EQUIPMENT | Medium Voltage | 0A | 18/08/2024 |  | 19/09/2024 | 19/09/2024 | 28/08/2024 |  |  | CJR | 25 | For Analysis |  | 2024-08-18 | 2050-01-01 | 2024-09-19 | 2024-09-19 | 2024-08-28 | 2050-01-01 | 22
397 | 398 | ALT-BDD-ELE-BT-1988 | Perno Partido Bandejas | EQUIPMENT | BESS | EQUIPMENT | Low Voltage AC | 0A | 18/08/2024 |  | 19/09/2024 | 19/09/2024 | 28/08/2024 |  |  | CJR | 25 | For Analysis |  | 2024-08-18 | 2050-01-01 | 2024-09-19 | 2024-09-19 | 2024-08-28 | 2050-01-01 | 22
416 | 417 | ATL-BDD-CC-IN-1915 | Condiciones de Concesión de Licencia de Uso SCADA | EQUIPMENT | BESS | EQUIPMENT | SCADA and PPC | 0A | 18/09/2024 |  | 18/09/2024 | 18/09/2024 | 08/10/2024 |  |  | CJR | 31 | For Analysis |  | 2024-09-18 | 2050-01-01 | 2024-09-18 | 2024-09-18 | 2024-10-08 | 2050-01-01 | 23
351 | 352 | ATL-BDD-CC-ET-1906 | DESCRIPCIÓN DEL SISTEMA SCADA | EQUIPMENT | BESS | EQUIPMENT | SCADA and PPC | 0A | 25/07/2024 |  | 10/09/2024 | 10/09/2024 | 23/08/2024 |  |  | CJR | 18 | For Analysis |  | 2024-07-25 | 2050-01-01 | 2024-09-10 | 2024-09-10 | 2024-08-23 | 2050-01-01 | 31
174 | 175 | ATL-BDD-ELE-DW-1702 | ALUMBRADO EXTERIOR PLANTA Y DETALLES | ELECTROMECHANICAL | BESS | ELECTROMECHANICAL | Lighting System | 0A | 08/08/2024 |  | 10/09/2024 | 10/09/2024 | 23/08/2024 |  |  | CJR | 18 | Non-compliant |  | 2024-08-08 | 2050-01-01 | 2024-09-10 | 2024-09-10 | 2024-08-23 | 2050-01-01 | 31
166 | 167 | ATL-BDD-ELE-MC-1623 | CS-MEMORIA CARGADOR Y BATERIAS | ELECTRICAL | BESS | ELECTRICAL | Switching Building | 0B | 30/06/2024 |  | 01/07/2024 | 09/09/2024 | 26/07/2024 |  |  | CJR | 0 | For Analysis |  | 2024-06-30 | 2050-01-01 | 2024-07-01 | 2024-09-09 | 2024-07-26 | 2050-01-01 | 32
18 | 19 | ATL-BDD-23134-ELE-ET-13 | FSS System | EQUIPMENT | BESS | EQUIPMENT | Rectifier / Battery | 0D | 13/05/2024 |  | 06/05/2024 | 04/09/2024 | 10/06/2024 |  |  | SUNGROW | 0 | For Analysis |  | 2024-05-13 | 2050-01-01 | 2024-05-06 | 2024-09-04 | 2024-06-10 | 2050-01-01 | 37
217 | 218 | ATL-BDD-23134-HSE-PR-02 | Plan de Emergencia | EQUIPMENT | BESS | EQUIPMENT | General | 0B | 12/06/2024 |  | 03/09/2024 | 03/09/2024 | 10/07/2024 |  |  | SUNGROW | 3 | Non-compliant |  | 2024-06-12 | 2050-01-01 | 2024-09-03 | 2024-09-03 | 2024-07-10 | 2050-01-01 | 38
327 | 328 | ATL-BDD-CIV-MC-1643 | CS - FUNDACION TRAFO SSAA (MC) | ELECTRICAL | BESS | ELECTRICAL | Auxiliary System | 0A | 08/08/2024 |  | 02/09/2024 | 02/09/2024 | 06/09/2024 |  |  | CJR | 18 | Non-compliant |  | 2024-08-08 | 2050-01-01 | 2024-09-02 | 2024-09-02 | 2024-09-06 | 2050-01-01 | 39
285 | 286 | ATL-BDD-23134-ELE-DW-06 | Single Line Diagram - PCS | EQUIPMENT | BESS | EQUIPMENT | Rectifier / Battery | 0C | 24/05/2024 |  | 22/06/2024 | 31/08/2024 | 13/06/2024 |  |  | SUNGROW | 6 | For Analysis |  | 2024-05-24 | 2050-01-01 | 2024-06-22 | 2024-08-31 | 2024-06-13 | 2050-01-01 | 41
282 | 283 | ATL-BDD-23134-ELE-ET-15 | Liquid Cooling System - Self Consumption 0_25C | EQUIPMENT | BESS | EQUIPMENT | Rectifier / Battery | 0C | 20/05/2024 |  | 29/05/2024 | 31/08/2024 | 09/06/2024 |  |  | SUNGROW | 5 | For Analysis |  | 2024-05-20 | 2050-01-01 | 2024-05-29 | 2024-08-31 | 2024-06-09 | 2050-01-01 | 41
378 | 379 | ALT-BDD-ELE-BT-1969 | TRANSFORMADOR ENCAPSULADO EN RESINA 33KV_100KVA | EQUIPMENT | BESS | EQUIPMENT | P&C System | 0A | 18/08/2024 |  | 27/08/2024 | 27/08/2024 | 28/08/2024 |  |  | CJR | 25 | For Analysis |  | 2024-08-18 | 2050-01-01 | 2024-08-27 | 2024-08-27 | 2024-08-28 | 2050-01-01 | 45
15 | 16 | ATL-BDD-23134-ELE-ET-10 | LC200 Datasheet | EQUIPMENT | BESS | EQUIPMENT | Rectifier / Battery | 0C | 13/05/2024 |  | 14/05/2024 | 27/08/2024 | 10/06/2024 |  |  | SUNGROW | 0 | For Analysis |  | 2024-05-13 | 2050-01-01 | 2024-05-14 | 2024-08-27 | 2024-06-10 | 2050-01-01 | 45
13 | 14 | ATL-BDD-23134-ELE-ET-08 | Battery Modules Datasheet | EQUIPMENT | BESS | EQUIPMENT | Rectifier / Battery | 0C | 29/03/2024 |  | 06/05/2024 | 27/08/2024 | 26/04/2024 |  |  | SUNGROW | 0 | For Analysis |  | 2024-03-29 | 2050-01-01 | 2024-05-06 | 2024-08-27 | 2024-04-26 | 2050-01-01 | 45
12 | 13 | ATL-BDD-23134-ELE-ET-07 | Cell Datasheet | EQUIPMENT | BESS | EQUIPMENT | Rectifier / Battery | 0C | 29/03/2024 |  | 06/05/2024 | 27/08/2024 | 26/04/2024 |  |  | SUNGROW | 0 | For Analysis |  | 2024-03-29 | 2050-01-01 | 2024-05-06 | 2024-08-27 | 2024-04-26 | 2050-01-01 | 45
10 | 11 | ATL-BDD-23134-ELE-ET-05 | DC-DC Datasheet | EQUIPMENT | BESS | EQUIPMENT | Rectifier / Battery | 0C | 29/03/2024 |  | 06/05/2024 | 27/08/2024 | 26/04/2024 |  |  | SUNGROW | 0 | For Analysis |  | 2024-03-29 | 2050-01-01 | 2024-05-06 | 2024-08-27 | 2024-04-26 | 2050-01-01 | 45
37 | 38 | ATL-BDD-23134-QAC-MN-05 | Transformer - Manual | EQUIPMENT | BESS | EQUIPMENT | Power Transformer | 0C | 28/04/2024 |  | 06/05/2024 | 26/08/2024 | 28/05/2024 |  |  | SUNGROW | 0 | For Analysis |  | 2024-04-28 | 2050-01-01 | 2024-05-06 | 2024-08-26 | 2024-05-28 | 2050-01-01 | 46
6 | 7 | ATL-BDD-23134-ELE-ET-01 | PCS SC5000UD-MV Datasheet | EQUIPMENT | BESS | EQUIPMENT | MV Equipment | 0C | 29/03/2024 |  | 06/05/2024 | 26/08/2024 | 26/04/2024 |  |  | SUNGROW | 0 | For Analysis |  | 2024-03-29 | 2050-01-01 | 2024-05-06 | 2024-08-26 | 2024-04-26 | 2050-01-01 | 46
9 | 10 | ATL-BDD-23134-ELE-ET-04 | Liquid Cooling ESS Datasheet | EQUIPMENT | BESS | EQUIPMENT | Rectifier / Battery | 0C | 29/03/2024 |  | 06/05/2024 | 26/08/2024 | 26/04/2024 |  |  | SUNGROW | 0 | For Analysis |  | 2024-03-29 | 2050-01-01 | 2024-05-06 | 2024-08-26 | 2024-04-26 | 2050-01-01 | 46
281 | 282 | ATL-BDD-23134-ELE-ET-14 | DC Fuses Datasheet | EQUIPMENT | BESS | EQUIPMENT | Rectifier / Battery | 00 | 20/05/2024 |  | 29/05/2024 | 19/08/2024 | 02/06/2024 |  | 03/10/2024 | SUNGROW | 5 | For revision |  | 2024-05-20 | 2050-01-01 | 2024-05-29 | 2024-08-19 | 2024-06-02 | 2050-01-01 | 53
77 | 78 | ATL-BDD-CIV-DW-1105 | ESTRUCTURA PARA-RAYOS. DETALLES | CIVIL | BESS | CIVIL | Minor Structures | 0A | 31/07/2024 |  | 16/08/2024 | 16/08/2024 | 30/08/2024 |  |  | CJR | 18 | For Analysis |  | 2024-07-31 | 2050-01-01 | 2024-08-16 | 2024-08-16 | 2024-08-30 | 2050-01-01 | 56
24 | 25 | ATL-BDD-23134-MEC-DW-02 | LC1000 - Mechanical Drawing | EQUIPMENT | BESS | EQUIPMENT | Rectifier / Battery | 0D | 28/04/2024 |  | 06/05/2024 | 13/08/2024 | 28/05/2024 |  |  | SUNGROW | 0 | For Analysis |  | 2024-04-28 | 2050-01-01 | 2024-05-06 | 2024-08-13 | 2024-05-28 | 2050-01-01 | 59
34 | 35 | ATL-BDD-23134-QAC-MN-02 | LC1000 - Manual | EQUIPMENT | BESS | EQUIPMENT | Rectifier / Battery | 0C | 28/04/2024 |  | 14/05/2024 | 10/08/2024 | 28/05/2024 |  |  | SUNGROW | 0 | For Analysis |  | 2024-04-28 | 2050-01-01 | 2024-05-14 | 2024-08-10 | 2024-05-28 | 2050-01-01 | 62
124 | 125 | ATL-BDD-ELE-LS-1422 | LISTADO DE CABLES DE COMUNICACIÓN | EQUIPMENT | BESS | EQUIPMENT | Communications | 0C | 07/06/2024 |  | 13/06/2024 | 08/08/2024 | 05/07/2024 |  |  | CJR | 0 | For Analysis |  | 2024-06-07 | 2050-01-01 | 2024-06-13 | 2024-08-08 | 2024-07-05 | 2050-01-01 | 64
206 | 207 | ATL-BDD-23134-COM-PR-01 | Cold Commissioning Procedure | EQUIPMENT | BESS | EQUIPMENT | Rectifier / Battery | 0B | 12/06/2024 |  | 02/08/2024 | 02/08/2024 | 10/07/2024 |  |  | SUNGROW | 3 | Non-compliant |  | 2024-06-12 | 2050-01-01 | 2024-08-02 | 2024-08-02 | 2024-07-10 | 2050-01-01 | 70
208 | 209 | ATL-BDD-23134-COM-PR-03 | Site Acceptance Test Procedure | EQUIPMENT | BESS | EQUIPMENT | Rectifier / Battery | 0B | 12/06/2024 |  | 02/08/2024 | 02/08/2024 | 10/07/2024 |  |  | SUNGROW | 3 | For Analysis |  | 2024-06-12 | 2050-01-01 | 2024-08-02 | 2024-08-02 | 2024-07-10 | 2050-01-01 | 70
329 | 330 | ATL-BDD-23134-MEC-MC-05 | FSS Hidraulic Calculation Report | EQUIPMENT | BESS | EQUIPMENT | Rectifier / Battery | 0B | 08/07/2024 |  | 17/07/2024 | 17/07/2024 | 22/07/2024 |  |  | SUNGROW | 15 | For Analysis |  | 2024-07-08 | 2050-01-01 | 2024-07-17 | 2024-07-17 | 2024-07-22 | 2050-01-01 | 86
330 | 331 | ATL-BDD-23134-CYC-DW-07 | FSS Wiring Diagram | EQUIPMENT | BESS | EQUIPMENT | Rectifier / Battery | 0B | 08/07/2024 |  | 17/07/2024 | 17/07/2024 | 22/07/2024 |  |  | SUNGROW | 15 | For Analysis |  | 2024-07-08 | 2050-01-01 | 2024-07-17 | 2024-07-17 | 2024-07-22 | 2050-01-01 | 86
349 | 350 | ATL-BDD-CC-PR-1904 | PROCEDIMIENTO DE PRUEBAS SAT | EQUIPMENT | BESS | EQUIPMENT | SCADA and PPC | 0A | 12/07/2024 |  | 13/07/2024 | 13/07/2024 | 14/08/2024 |  |  | CJR | 16 | Non-compliant |  | 2024-07-12 | 2050-01-01 | 2024-07-13 | 2024-07-13 | 2024-08-14 | 2050-01-01 | 90
350 | 351 | ATL-BDD-CC-MN-1905 | MANUAL DE USUARIO DEL SISTEMA SCADA | EQUIPMENT | BESS | EQUIPMENT | SCADA and PPC | 0A | 12/07/2024 |  | 13/07/2024 | 13/07/2024 | 14/08/2024 |  |  | CJR | 16 | Non-compliant |  | 2024-07-12 | 2050-01-01 | 2024-07-13 | 2024-07-13 | 2024-08-14 | 2050-01-01 | 90
348 | 349 | ATL-BDD-CC-PR-1903 | PROCEDIMIENTO DE PRUEBAS FAT | EQUIPMENT | BESS | EQUIPMENT | SCADA and PPC | 0A | 12/07/2024 |  | 13/07/2024 | 13/07/2024 | 14/08/2024 |  |  | CJR | 16 | Non-compliant |  | 2024-07-12 | 2050-01-01 | 2024-07-13 | 2024-07-13 | 2024-08-14 | 2050-01-01 | 90
324 | 325 | ATL-BDD-ELE-DW-1428 | DETALLE CONEXION BARRA DE 33 kV (PARRÓN) | ELECTRICAL | BESS | ELECTRICAL | General | 0A | 04/07/2024 |  | 12/07/2024 | 12/07/2024 | 01/08/2024 |  |  | CJR | 15 | Non-compliant |  | 2024-07-04 | 2050-01-01 | 2024-07-12 | 2024-07-12 | 2024-08-01 | 2050-01-01 | 91
196 | 197 | ATL-BDD-23134-QAC-PT-02 | Inspection Report - Template - Battery Module | EQUIPMENT | BESS | EQUIPMENT | Rectifier / Battery | 00 | 13/05/2024 |  | 09/05/2024 | 08/07/2024 | 10/06/2024 |  | 30/07/2024 | SUNGROW | 3 | Cancelled |  | 2024-05-13 | 2050-01-01 | 2024-05-09 | 2024-07-08 | 2024-06-10 | 2050-01-01 | 95
33 | 34 | ATL-BDD-23134-QAC-MN-01 | Liquid Cooling ESS - Manual | EQUIPMENT | BESS | EQUIPMENT | Rectifier / Battery | 0C | 28/04/2024 |  | 06/05/2024 | 04/07/2024 | 28/05/2024 |  |  | SUNGROW | 0 | For Analysis |  | 2024-04-28 | 2050-01-01 | 2024-05-06 | 2024-07-04 | 2024-05-28 | 2050-01-01 | 99
75 | 76 | ATL-BDD-CIV-DW-1103 | CIMENTACIONES PCS. DETALLES | CIVIL | BESS | CIVIL | Minor Foundations | 00 | 05/07/2024 |  | 17/06/2024 | 04/07/2024 | 02/08/2024 |  |  | CJR | 0 | For revision |  | 2024-07-05 | 2050-01-01 | 2024-06-17 | 2024-07-04 | 2024-08-02 | 2050-01-01 | 99
76 | 77 | ATL-BDD-CIV-DW-1104 | CIMENTACIONES GABINETE y TRAFO SSAA. DETALLES | CIVIL | BESS | CIVIL | Minor Foundations | 00 | 05/07/2024 |  | 22/05/2024 | 04/07/2024 | 02/08/2024 |  |  | CJR | 0 | For revision |  | 2024-07-05 | 2050-01-01 | 2024-05-22 | 2024-07-04 | 2024-08-02 | 2050-01-01 | 99
80 | 81 | ATL-BDD-CIV-MC-1108 | CIMENTACIONES GABINETE y TRAFO SSAA. MEMORIA DE CÁLCULO | CIVIL | BESS | CIVIL | Minor Foundations | 00 | 05/07/2024 |  | 27/05/2024 | 04/07/2024 | 02/08/2024 |  |  | CJR | 0 | For revision |  | 2024-07-05 | 2050-01-01 | 2024-05-27 | 2024-07-04 | 2024-08-02 | 2050-01-01 | 99
26 | 27 | ATL-BDD-23134-ELE-DW-04 | Single Line Diagram - ESS System | EQUIPMENT | BESS | EQUIPMENT | Rectifier / Battery | 0C | 28/04/2024 |  | 02/05/2024 | 03/07/2024 | 28/05/2024 |  |  | SUNGROW | 0 | For Analysis |  | 2024-04-28 | 2050-01-01 | 2024-05-02 | 2024-07-03 | 2024-05-28 | 2050-01-01 | 100
300 | 301 | ATL-BDD-23134-ELE-ET-16 | PCS P-Q Diagram | EQUIPMENT | BESS | EQUIPMENT | Rectifier / Battery | 0C | 14/06/2024 |  | 17/06/2024 | 03/07/2024 | 04/07/2024 |  |  | SUNGROW | 10 | For Analysis |  | 2024-06-14 | 2050-01-01 | 2024-06-17 | 2024-07-03 | 2024-07-04 | 2050-01-01 | 100
27 | 28 | ATL-BDD-23134-ELE-DW-05 | General Wiring Layout | EQUIPMENT | BESS | EQUIPMENT | Rectifier / Battery | 0B | 13/05/2024 |  | 18/06/2024 | 18/06/2024 | 10/06/2024 |  |  | SUNGROW | 0 | For Analysis |  | 2024-05-13 | 2050-01-01 | 2024-06-18 | 2024-06-18 | 2024-06-10 | 2050-01-01 | 115
284 | 285 | ATL-BDD-23134-ELE-MC-04 | PCS - Short-circuit Level Calculation | EQUIPMENT | BESS | EQUIPMENT | Rectifier / Battery | 0B | 14/06/2024 |  | 17/06/2024 | 17/06/2024 | 04/07/2024 |  |  | SUNGROW | 9 | For Analysis |  | 2024-06-14 | 2050-01-01 | 2024-06-17 | 2024-06-17 | 2024-07-04 | 2050-01-01 | 116
286 | 287 | ATL-BDD-23134-QAC-MN-11 | LC1000 - UPS Manual | EQUIPMENT | BESS | EQUIPMENT | Rectifier / Battery | 0B | 24/05/2024 |  | 11/06/2024 | 11/06/2024 | 13/06/2024 |  |  | SUNGROW | 6 | For Analysis |  | 2024-05-24 | 2050-01-01 | 2024-06-11 | 2024-06-11 | 2024-06-13 | 2050-01-01 | 122
14 | 15 | ATL-BDD-23134-ELE-ET-09 | LC1000 Technical documentation | EQUIPMENT | BESS | EQUIPMENT | Rectifier / Battery | 0C | 13/05/2024 |  | 14/05/2024 | 07/06/2024 | 10/06/2024 |  |  | SUNGROW | 0 | For Analysis |  | 2024-05-13 | 2050-01-01 | 2024-05-14 | 2024-06-07 | 2024-06-10 | 2050-01-01 | 126
283 | 284 | ATL-BDD-23134-PLA-LS-01 | List of Deliverables Documents | EQUIPMENT | BESS | EQUIPMENT | General | 0F | 29/03/2024 |  | 07/05/2024 | 07/06/2024 | 26/04/2024 |  |  | SUNGROW | 5 | For Analysis |  | 2024-03-29 | 2050-01-01 | 2024-05-07 | 2024-06-07 | 2024-04-26 | 2050-01-01 | 126
41 | 42 | ATL-BDD-23134-QAC-MN-10 | Switch Ethernet Manual | EQUIPMENT | BESS | EQUIPMENT | Rectifier / Battery | 0C | 28/04/2024 |  | 29/05/2024 | 03/06/2024 | 28/05/2024 |  |  | SUNGROW | 0 | For Analysis |  | 2024-04-28 | 2050-01-01 | 2024-05-29 | 2024-06-03 | 2024-05-28 | 2050-01-01 | 130
133 | 134 | ATL-BDD-ELE-ET-1500 | ESPECIFICACIÓN CELDAS MT | EQUIPMENT | BESS | EQUIPMENT | MV Equipment | 00 | 30/04/2024 |  | 02/05/2024 | 29/05/2024 | 28/05/2024 |  | 13/06/2024 | CJR | 0 | For revision |  | 2024-04-30 | 2050-01-01 | 2024-05-02 | 2024-05-29 | 2024-05-28 | 2050-01-01 | 135
98 | 99 | ATL-BDD-CIV-DW-1436 | PLANO DE DEMOLICIONES Y CANALIZACIONES MT. DETALLES | ELECTROMECHANICAL | BESS | ELECTROMECHANICAL | Ducts/channels/cable trays | 0A | 02/07/2024 |  | 24/05/2024 | 24/05/2024 | 30/07/2024 |  |  | CJR | 15 | Non-compliant |  | 2024-07-02 | 2050-01-01 | 2024-05-24 | 2024-05-24 | 2024-07-30 | 2050-01-01 | 140
39 | 40 | ATL-BDD-23134-QAC-MN-08 | DC-DC Manual | EQUIPMENT | BESS | EQUIPMENT | Rectifier / Battery | 0B | 28/04/2024 |  | 06/05/2024 | 06/05/2024 | 28/05/2024 |  |  | SUNGROW | 0 | Non-compliant |  | 2024-04-28 | 2050-01-01 | 2024-05-06 | 2024-05-06 | 2024-05-28 | 2050-01-01 | 158
35 | 36 | ATL-BDD-23134-QAC-MN-03 | PCS - Manual | EQUIPMENT | BESS | EQUIPMENT | Power Transformer | 0B | 28/04/2024 |  | 06/05/2024 | 06/05/2024 | 28/05/2024 |  |  | SUNGROW | 0 | Non-compliant |  | 2024-04-28 | 2050-01-01 | 2024-05-06 | 2024-05-06 | 2024-05-28 | 2050-01-01 | 158